## App Lock Features
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | User Authentication | Authentication | As a user, I want to securely access the app lock features. | Must | In Progress | 1. User can register and login securely. 2. Authentication errors handled gracefully. | Secure password hashing, login attempts limited. | Authentication within 2 seconds. Secure data storage. | 3 days | 2 days
2 | Gambling App Detection | Tracking | As a user, I want gambling apps to be automatically detected and listed for tracking. | Must | Ready for Dev | 1. Gambling apps automatically detected. 2. User notified when gambling apps are added. | Detect gambling apps based on keywords and category. Notify user if gambling apps are detected. | Detection algorithm should have minimal false positives. Update list regularly. | 5 days | 5 days
3 | App Locking Mechanism | Security | As a user, I want the option to lock specific apps with a PIN, fingerprint, or pattern. | Must | In Testing | 1. User can set a lock type (PIN/Fingerprint/Pattern). 2. Lock activates after set time. | Implement PIN, fingerprint, and pattern lock options. Settings for auto-lock timer. | Locks should activate within 1 second. High reliability for lock function. | 7 days
4 | Access Logging | Tracking | As an admin, I want all attempts to access locked apps to be logged with timestamps. | Should | Backlog | 1. Each access attempt logged with timestamp and result. 2. Logs accessible by admin. | Record each attempt to access locked apps, including timestamps and access results. | Access logs stored securely and available within 24 hours. | 4 days
5 | Notification System | User Engagement | As a user, I want to receive alerts when a gambling app is accessed or unlocked. | Should | Backlog | 1. User receives notification for gambling app access. 2. Alerts configurable in settings. | Generate push notifications or SMS for gambling access attempts. User configurable settings. | Notifications should arrive within 5 seconds of access attempt. | 2 days
6 | Bug Fixes | Bug Fixes | Bug Fixes | As a user, I want a bug-free experience. | Must | In Progress | 1. Resolved login error for users with special characters in passwords 2. Fixed image loading issue in the gallery. 3. Regression testing confirms bug resolution. | Identify and fix specific bugs reported by users and testing. Implement automated tests to prevent regression. | Critical bugs should be resolved within 48 hours of discovery. Implement a bug-tracking system for efficient reporting and resolution. | 7 days