## Sprint Retrospective
Category | Feedback | Guidelines
Liked | The team appreciated the streamlined user authentication, responsive locking features, and ease of use of Mind Master. Users found the locking mechanisms intuitive and secure. | Continue enhancing authentication methods and refining locking mechanisms to ensure a smooth and secure user experience.
Learned | Realized that detecting gambling apps requires frequent updates to keep up with new gambling platforms and avoid false positives. Tracking accuracy improved significantly through incremental testing. | Implement regular updates to Mind Master's gambling app detection algorithms to maintain high accuracy. Scheduled checks and updates can further improve reliability.
Lacked | Mind Master lacked a real-time notification system for gambling app access due to limited time, which could have enhanced user alerts. This feature was deferred for future sprints. | Prioritize planning for real-time notification features in upcoming sprints to improve user awareness of gambling app access attempts.
Longed For | Desired more automation in the gambling app detection process to reduce manual updates and a more comprehensive integration with device security settings. | Explore AI-based detection in Mind Master for identifying gambling-related apps. Additionally, seek better integration with device-level security to support automatic blocking and alerts.